FoxAI DATA PLATFORM

Customer Deployment Plan

From bare server to working data mart, dashboard, and Excel export in 1 week

# Pre-conditions Before Day 1

The 1-week timeline only holds if all of the following are confirmed and ready before the engagement starts. Any of these missing on Day 1 will delay the schedule.

| Item | Requirement | Status |
| --- | --- | --- |
| Server access | Linux servers provisioned, SSH access granted, sudo permissions available | Must confirm before start |
| Server specs | Minimum 16GB RAM per node, sufficient disk for data volume, Java + Python installed | Must confirm before start |
| Network | No firewall blocking required ports (MinIO, Spark, Kafka, Airflow) | Must confirm before start |
| Sample data | Representative sample of customer data provided in final format before Day 1 | Must confirm before start |
| Schema & requirements | Data fields documented, dashboard charts agreed, data mart structure defined, Excel format specified | Must confirm before start |
| Data contact | Someone on customer side available same-day to answer data questions | Must confirm before start |

⚠️ If requirements are not locked before Day 1: Do not start the engagement. Scope changes mid-week are the single biggest cause of delivery failure. Dashboard charts, data mart structure, and Excel format must be agreed and signed off in advance.

# Week Schedule — Day by Day

| Day 1 Monday Infrastructure | - Deploy core stack: MinIO, Apache Spark, Kafka, Airflow on customer servers - Configure S3A connection between Spark and MinIO - Set up Iceberg catalog (HadoopCatalog) pointing to MinIO buckets - Create bucket structure: raw / bronze / silver / gold - Deploy Airflow, confirm DAG folder is connected and scheduler is running - Run end-to-end smoke test: Spark reads from MinIO, writes an Iceberg table, Airflow triggers a test DAG ✅ End of day: Full cluster is up. Spark, Kafka, MinIO, Airflow all running and connected. Smoke test passes. |
| --- | --- |

| Day 2 Tuesday Data Ingestion | - Inspect customer sample data: format, schema, encoding, null patterns, date formats - Define Bronze schema: field names, types, partition strategy - Write and test Bronze ingestion pipeline — load customer data into MinIO Bronze layer as Iceberg table - Validate Bronze output: row counts match source, schema correct, no data loss - Document any data quality issues found (nulls, bad values, unexpected formats) - Confirm with customer data contact on any ambiguous fields ✅ End of day: Customer data fully loaded into Bronze Iceberg table on MinIO. Schema documented. Data quality issues logged. |
| --- | --- |

| Day 3 Wednesday Silver Pipeline | - Define Silver cleaning rules based on Day 2 findings - Write Silver transformation pipeline: clean nulls, standardize formats, remove invalid rows, compute derived fields - Ensure Silver pipeline is deterministic and idempotent — safe to rerun - Validate Silver output: null rates, duplicate rates, schema consistency - Log input row count, output row count, rejected rows with reasons - Fix any edge cases discovered during validation ✅ End of day: Silver Iceberg table ready. Clean, validated data available for Gold layer. Pipeline reruns safely. |
| --- | --- |

| Day 4 Thursday Gold & Export | - Define Gold aggregations based on agreed data mart structure - Write Gold pipeline: business-level aggregations, KPIs, summary tables - Schedule all pipelines in Airflow: Bronze → Silver → Gold runs automatically - Write Excel export job: pull from Gold tables, format and export to .xlsx - Test full automated run end-to-end: trigger Airflow DAG, confirm Gold updates, confirm Excel exports - Verify data mart output matches expected business logic with customer data contact ✅ End of day: Gold data mart ready. Excel export working. Full pipeline runs end-to-end on schedule via Airflow. |
| --- | --- |

| Day 5 Friday Dashboard & Handover | - Set up Apache Superset, connect to Gold Iceberg tables - Build agreed dashboards: charts, filters, KPI panels - Walk customer through dashboard and data mart — live demo - Collect feedback, apply revision round - Hand over: access credentials, pipeline runbook, how to trigger reruns, how to export Excel - Confirm customer can access everything independently ✅ End of day: Dashboards live. Customer signed off. Runbook delivered. Engagement complete. |
| --- | --- |

# Week at a Glance

| Day | Focus | Key Output |
| --- | --- | --- |
| Day 1 — Monday | Infrastructure | Cluster running: Spark + Kafka + MinIO + Airflow + Iceberg |
| Day 2 — Tuesday | Data Ingestion | Customer data in Bronze Iceberg table, schema documented |
| Day 3 — Wednesday | Silver Pipeline | Clean Silver layer, validated, idempotent, logged |
| Day 4 — Thursday | Gold & Export | Data mart ready, Excel export working, pipeline scheduled |
| Day 5 — Friday | Dashboard & Handover | Superset dashboards live, customer signed off, runbook delivered |

# Risk & Buffer

Even with all pre-conditions met, some tasks commonly run over. The schedule above has natural buffer built in — Day 4 and Day 5 are less dense to absorb spillover from earlier days.

| Risk | Most likely day it hits | Mitigation |
| --- | --- | --- |
| Data quality worse than sample suggests | Day 2-3 | Document and log all issues — fix what blocks pipeline, defer cosmetic issues to post-delivery |
| Dashboard revision scope expands | Day 5 | Agree on maximum 2 revision rounds — additional changes go to a post-delivery ticket |
| Server permission or network issue | Day 1 | Resolve before start — do not begin deployment without SSH and port access confirmed |
| Customer data contact unavailable | Day 2-3 | Get all schema questions answered on Day 1 before data work begins |

— End of Deployment Plan —

FoxAI Data Platform  ·  Customer Deployment  ·  Confidential