FoxAI DATA PLATFORM

Implementation Plan

Start: 13 May 2026   ·   Deadline: 31 May 2026   ·   1 Developer

| Features | 1. Licensing (Online Key Validation) 2. Packaging (Linux only) 3. Plugin Architecture (CustomTransformer v1) |
| --- | --- |
| Start | Wednesday, 13 May 2026 |
| Deadline | Sunday, 31 May 2026 (19 calendar days / ~13 working days) |
| Team | 1 developer |
| Out of scope | Real-time / Drone processing, Windows / Docker deployment, all plugin types except CustomTransformer |

# 1. Licensing — Online Key Validation

## Approach

Integrate with the other team's existing licensing system via their provided API. On FoxAI startup, the core reads the local license key file and sends it to the licensing server for validation. The response determines: whether the key is valid, its expiry date, and the allowed tier (which controls DataNode count). FoxAI boots normally if valid, refuses to start if not.

## Why This Approach

- The licensing server and key management is owned by the other team — we only consume it, no need to build our own server

- Keeps our scope minimal: one API call on startup, enforce the response, done

- Tier-based node limits (Basic = 3 nodes, Pro = 7 nodes) are returned in the API response and enforced by FoxAI core

- 1-year subscription expiry is handled server-side by the other team — we just check the returned expiry date

Key Design Decisions • Grace period: if the licensing server is unreachable, FoxAI allows up to 72 hours of continued operation before blocking — avoids service disruption from temporary network issues • License key stored locally at: /etc/foxai/license.key — customer places this file after purchase • Node enforcement: when a new DataNode tries to register, NameNode checks current count against the tier limit and rejects if exceeded

## Completion Date

| Task | Date |
| --- | --- |
| Integrate licensing API call into FoxAI startup module | 14 May |
| Implement tier enforcement (node count limit) | 15 May |
| Grace period logic + error messaging | 16 May |
| Testing all pass/fail/grace scenarios | 19 May |

✅  Feature 1 complete by:  19 May 2026

# 2. Packaging — Linux Binary Distribution

## Approach

Core FoxAI Python modules (pipeline scripts, license enforcement, histogram logic) are compiled into native Linux binary files (.so) using Cython. Customers receive these binaries — they can run them but cannot read or modify the source code. Deployment is automated by a shell installer script (install.sh) that sets up the full stack on a fresh Linux server.

## Why This Approach

- Linux-only: matches our current server infrastructure exactly, no platform conflicts

- Cython compilation is the industry standard for protecting Python code — produces .so binaries that are not human-readable

- Shell installer removes manual setup burden from the customer — one script handles everything

- No Docker, no Windows: keeps scope clean and avoids significant additional complexity for this deadline

What Gets Compiled vs What Stays Plain COMPILED (.so): silver.py, gold.py, silver_histograms.py, license enforcement module, all DAG files PLAIN (kept readable): plugin interface base classes (customers must read these), config files (.json / .yaml), install.sh

## Completion Date

| Task | Date |
| --- | --- |
| Set up Cython build pipeline, compile first module as proof of concept | 20 May |
| Compile all core modules, run full test suite against binaries | 21 May |
| Write and test install.sh — deploys full stack on a fresh Linux VM | 22 May |
| End-to-end test: clean VM + installer + compiled binaries + license key → pipeline runs | 26 May |

✅  Feature 2 complete by:  26 May 2026

# 3. Plugin Architecture — CustomTransformer v1

## Approach

The core exposes a BaseTransformer interface — a Python base class with two required methods customers must implement. Customers write their own transformer class, drop the file into /opt/foxai/plugins/, and FoxAI automatically discovers and runs it inside the Silver processing stage. Invalid or broken plugins are skipped with a clear error log — they cannot crash the core pipeline.

## Why This Approach

- CustomTransformer only for v1 — the most immediately useful plugin type, covers the majority of customer customization needs

- File-drop discovery (no registration step needed) keeps the customer experience simple

- Error isolation is non-negotiable: a bad plugin must never break the core pipeline

- BaseTransformer file is intentionally kept as plain Python (not compiled) — customers need to read it to write their own plugins

Plugin Contract (What Customer Must Implement) transform(df: DataFrame) → DataFrame — Custom Silver-layer transformation logic on a Spark DataFrame validate_config(config: dict) → bool — Validates plugin config before transform() is called A working example plugin (taxi domain transformer) is delivered alongside as reference.

## Completion Date

| Task | Date |
| --- | --- |
| Design and write BaseTransformer interface + plugin loader/discovery module | 27 May |
| Integrate plugin loader into Silver pipeline, write example plugin, integration test | 28 May |
| SDK documentation + final full-system smoke test (all 3 features together) | 29 May |

✅  Feature 3 complete by:  29 May 2026

# Timeline Overview

Grey = weekend. Red = deadline (31 May).

| Task | 13/5 | 14/5 | 15/5 | 16/5 | 17/5 | 18/5 | 19/5 | 20/5 | 21/5 | 22/5 | 23/5 | 24/5 | 25/5 | 26/5 | 27/5 | 28/5 | 29/5 | 30/5 | 31/5 |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| LICENSING |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| API integration + startup module |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Tier / node enforcement |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Grace period + error handling |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Testing |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| PACKAGING |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Cython build pipeline + first compile |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Compile all core modules + tests |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Write install.sh |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| End-to-end clean install test |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| PLUGIN ARCHITECTURE |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| BaseTransformer + loader |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Silver integration + example plugin |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| SDK docs + smoke test |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| BUFFER / DEADLINE |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Emergency buffer + final handover |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |

Legend:  ■ Licensing   ■ Packaging   ■ Plugin   ■ Buffer / Deadline   ■ Weekend

— End of Plan —